## RAID Log
Risk: Events that could potetially impact the project's execution or workflow.
Action Strategies, plans or activities within the project lifecycle
Asumptions: Factors that are considered to be true, real or certain without any proof and demonstration
Issue: represent event or conditions that have already occurred, potentially leading to problems in the projects execution.
Decision: are choices made and managed throughout a project’s lifecycle.
Dependency: Plans or actions to take the project forward.
ID | Date Entered | Entered by | ADV/Tiger/Deloitte/Panama | RAID Category | Priority | Description | Impact (list impacted milestone) | Mitigation Plan/Action Plan | Due by | Owner | Status | Status Commentary
| 2024-10-24 | Atul | Tiger | Decision | High | Metadata Persistence - where and how should metadata be created and managed - use of JSON, DB Tables, or Both | V2 | Decision has been made manage in JSON files | 2024-10-25 | Tim Lam | Closed | Please refer to https://advantagesolutionsnet.sharepoint.com/:x:/r/sites/DataLakePlatform/Shared%20Documents/Data%20and%20Analytics%20Platform%20-%20Shared%20Documentation/Design%20Documents/General%20%26%20Non-Stage%20Specific/Foundation%20And%20Architecture/Orchestration/EnggFrameworkMetadata.xlsx?d=w189f98a06f184f1e93651dcacdeaa945&csf=1&web=1&e=O8d523
| 2024-10-24 | Atul | Tiger | Decision | Medium | Metadata Persistence - where and how should metadata be created and managed - use of JSON, DB Tables, or Both - Execution Metadata including logs and metrics | V2 | Decision has to be made if custom Execution Metadata is required and where should it be persisted | 2024-10-25 | Tim Lam | Closed | We will not capture any Execution Metadata in v2 of the framework - instead rely on the metadata captured within Databricks. Please refer to https://advantagesolutionsnet.sharepoint.com/:x:/r/sites/DataLakePlatform/Shared%20Documents/Data%20and%20Analytics%20Platform%20-%20Shared%20Documentation/Design%20Documents/General%20%26%20Non-Stage%20Specific/Foundation%20And%20Architecture/Orchestration/EnggFrameworkMetadata.xlsx?d=w189f98a06f184f1e93651dcacdeaa945&csf=1&web=1&e=O8d523
| 2024-10-24 | Atul | Tiger | Decision | Medium | Use of Enterprise Orchestration Tool | V2 |  | 2024-11-01 | Trevor, Koti | Closed | Will be taken up in v3 of the framework
| 2024-10-24 | Atul | Tiger | Assumption | Medium | There are only two source types - File Shares (Azure Blob, AWS S3, etc.) and Databricks Catalogs | V2 |  | 2024-11-01 | Tim Lam | Closed
| 2024-10-25 | Tejeswi | Tiger | Decision | Medium | Bronze layer tables(DLT/non DLT) are within framework scope, and for silver and gold layer whether it can be DLT/non DLT is upto Use case team to decide | V2 | Decision has been proposed and should be finalised | 2024-10-29 | Tim Lam | Closed
| 2024-10-25 | Tejeswi | Tiger | Decision | Medium | As integrated M3/M2 code is not available, we are considering M3 as base code for customisation / enhancements and provided in code repo ' Tiger-Ecif-M3' | V2 | These codechanges can later be integrated into main framework repo | 2024-11-01 | Tim Lam | Closed
| 2024-10-28 | Tejeswi | Tiger | Risk | Low | Watermark value being retrieved dynamically from target table will have performance issue | V2 | An alternate design is being looked into whereby a query on the existing bronze tables may not be needed | 2024-11-26 | Tim Lam | Closed
| 2024-10-28 | Tejeswi | Tiger | Decision | Medium | Enable/Disable flag for a particular table/layer cannot be implemented without code changes (CI/CD process) | V2 |  | 2024-11-26 | Tim Lam | Closed
| 2024-10-28 | Tejeswi | Tiger | Decision | High | Ingestion framework will work with raw and bronze layer for mass ingestion. | V2 |  | 2024-11-08 | Trevor, Koti, Tim | Closed | Refer to https://advantagesolutionsnet.sharepoint.com/:x:/r/sites/DataLakePlatform/_layouts/15/Doc.aspx?sourcedoc=%7B8C3678C3-4197-4E82-9A72-3EDF0BBDABEA%7D&file=Medallion-Processing-Scenarios.xlsx&action=default&mobileredirect=true
| 2024-10-28 | Tejeswi | Tiger | Decision | High | Enhanced Json metadata model proposed by Tiger team will be used for the framework. New json parser and other helper functions supporting this will be done. | V2 |  | 2024-11-05 | Tim Lam | Closed
| 2024-11-07 | Tyler | ADV | Risk | High | CI/CD automation using Github Actions is not fully resolved yet and there is a dependency on EA team to provide a solution or an alternative. This is needed to promote data pipelines from DEV to PROD. | V2 | Arch Team is planning to work with Databricks SMEs to solve for Github Actions blocker and suggest an alternative as Azure DevOps if the former design does not work | 2024-11-22 | Trevor, Koti | Closed | A solution using ADO and Github is in place and will be rolled out soon
| 2024-11-06 | Atul | Tiger | Decision | High | Raw tier will be added to the Medallion architecture where data snapshot and CDC tables will be hosted | V2 | This design has been reviwed with both ADV architecture and DE | 2024-11-08 | Trevor, Koti, Tim | Closed
| 2024-11-11 | Atul | Tiger | Decision | High | While the framework is capable of implementing SCD1 or SCD2 history tracking in Bronze tier, how the pattern must be identified and who does that, needs to be decided. | V2 | Decision is to implement SCD2 by default in the Bronze tier. This can be revisited based on first few batches of pipelines. | 2024-11-15 | Trevor, Tim | Closed
| 2024-11-11 | Atul | Tiger | Decision | High | Can Databricks time travel and versioning capability be used instead of explicit code based implementation of SCD1 and SCD2. | V2 | Per advice from Databricks SMEs, this capability should only be used for troubleshooting and not as a substitute for data warehouse history tracking using SCD patterns | 2024-11-16 | Trevor, Tim | Closed
| 2024-11-15 | Atul | Tiger | Decision | Medium | Will be discussing and implementing a few changes in V2.1 of the framework - focussed on a few issues including use of Audit table | V2.1 |  | 2024-11-22 | Tim Lam | Closed
| 2024-11-27 | Tejeswi | Tiger | Decision | Low | Existing audit log functionality in V2.0 will be removed in v2.1 code changes | V2 |  |  |  | Closed
| 2024-11-27 | Tejeswi | Tiger | Risk | Medium | Implemented watermark logic will have a performance impact | V2 |  |  |  | Closed
| 2024-12-27 | Atul | Tiger | Decision | High | Redwood to be used for enterprise scheduling while the process orchestration to continue to be based on Databricks Workflows and DLTs (and not Airflow) | V3 |  |  |  | Closed | Decision approved by Trevor
| 2025-03-07 | Suresh | Tiger | Dependency | Medium | Python whl package - ci/cd integration and automate process of whl package deployment | V3 | we need permission to Creating a New Artifact Feed in Azure DevOps |  |  | Open
| 2025-03-26 | Atul | Tiger | Issue | High | Disabled access for offshore foundation team members | V3 | Tickets have been opened and multiple follow ups have been happening |  |  | Open
| 2025-03-28 | Atul | Tiger | Risk | High | With Tyler leaving at same time as TA contract concluding, a lot of knowledge is walking out door at same time. | V3 |  |  |  | Open

## Values
Category | Priority | Status
Risk | High | Open | ADV
Issue | Medium | Closed | Tiger
Assumption | Low |  | Deloitte
Action Item |  |  | Panama
Dependency
Decision
Interdependency